## Test Scenarios
Login Module
Scenario ID | Module | Test Scenario | Priority
TS-001 | Login | Verify login with valid credentials | High
TS-002 | Login | Verify login with invalid username | High
TS-003 | Login | Verify login with invalid password | High
TS-004 | Login | Verify login with invalid username and password | High
TS-005 | Login | Verify login with empty username | Medium
TS-006 | Login | Verify login with empty password | Medium
TS-007 | Login | Verify login with both username and password empty | High
TS-008 | Login | Verify error message for invalid login | High
TS-009 | Login | Verify locked out user cannot log in | High
TS-010 | Login | Verify password field masks entered characters | Low
Product Module
Scenario ID | Module | Test Scenario | Priority
TS-011 | Products | Verify products are displayed after login | High
TS-012 | Products | Verify product name is displayed | Medium
TS-013 | Products | Verify product image is displayed | Medium
TS-014 | Products | Verify product price is displayed | Medium
TS-015 | Products | Verify product description is displayed | Low
TS-016 | Products | Verify Add to Cart button works | High
TS-017 | Products | Verify Remove button works after adding a product | High
TS-018 | Products | Verify multiple products can be added to cart | High
TS-019 | Products | Verify shopping cart badge updates correctly | High
TS-020 | Products | Verify product sorting by Name (A–Z) | Medium
TS-021 | Products | Verify product sorting by Name (Z–A) | Medium
TS-022 | Products | Verify product sorting by Price (Low to High) | Medium
TS-023 | Products | Verify product sorting by Price (High to Low) | Medium
Shopping Cart Module
Scenario ID | Module | Test Scenario | Priority
TS-024 | Cart | Verify added product appears in cart | High
TS-025 | Cart | Verify product details are correct in cart | High
TS-026 | Cart | Verify Remove button removes the product | High
TS-027 | Cart | Verify Continue Shopping button redirects correctly | Medium
TS-028 | Cart | Verify Checkout button redirects to checkout page | High
TS-029 | Cart | Verify multiple added products are displayed | Medium
Checkout Information Module
Scenario ID | Module | Test Scenario | Priority
TS-030 | Checkout | Verify checkout with valid information | High
TS-031 | Checkout | Verify checkout with empty first name | High
TS-032 | Checkout | Verify checkout with empty last name | High
TS-033 | Checkout | Verify checkout with empty postal code | High
TS-034 | Checkout | Verify checkout with all fields empty | High
TS-035 | Checkout | Verify Cancel button returns to cart | Medium
Checkout Overview Module
Scenario ID | Module | Test Scenario | Priority
TS-036 | Overview | Verify product information is displayed | High
TS-037 | Overview | Verify payment information is displayed | Medium
TS-038 | Overview | Verify shipping information is displayed | Medium
TS-039 | Overview | Verify tax amount is displayed | Medium
TS-040 | Overview | Verify total amount is calculated correctly | High
TS-041 | Overview | Verify Finish button completes the order | High
TS-042 | Overview | Verify Cancel button returns to products page | Medium
Order Confirmation Module
Scenario ID | Module | Test Scenario | Priority
TS-043 | Confirmation | Verify order success message is displayed | High
TS-044 | Confirmation | Verify Back Home button redirects to products page | Medium
Navigation Menu
Scenario ID | Module | Test Scenario | Priority
TS-045 | Menu | Verify menu opens successfully | Medium
TS-046 | Menu | Verify menu closes successfully | Low
TS-047 | Menu | Verify All Items option redirects correctly | Medium
TS-048 | Menu | Verify About option opens the correct page | Low
TS-049 | Menu | Verify Logout option logs out the user | High
TS-050 | Menu | Verify Reset App State resets the cart | Medium

## Test Cases
Login Test Cases
Test Case ID | Scenario ID | Module | Test Case Description | Test Steps | Test Data | Expected Result | Actual Result | Status
TC-001 | TS-001 | Login | Verify login with valid credentials | 1. Open SauceDemo login page 2. Enter username 3. Enter password 4. Click Login button | Username: standard_user , Password: secret_sauce | User should successfully login and navigate to Products page | User logged in successfully and redirected to Products page. | Pass
TC-002 | TS-002 | Login | Verify login with invalid username | 1. Open login page 2. Enter invalid username 3. Enter valid password 4. Click Login | Username: invalid_user , Password: secret_sauce | Error message should be displayed | Error message "Username and password do not match any user in this service" was displayed. | Pass
TC-003 | TS-003 | Login | Verify login with invalid password | 1. Enter valid username 2. Enter incorrect password 3. Click Login | Username: standard_user , Password: wrong123 | Error message should be displayed | Error message "Username is required" was displayed. | Pass
TC-004 | TS-004 | Login | Verify login with invalid username and password | 1. Enter invalid username 2. Enter invalid password 3. Click Login | Username: test123 , Password: wrong123 | Error message should appear | Error message "Username and password do not match any user in this service" was displayed for invalid username and password. | Pass
TC-005 | TS-005 | Login | Verify login with empty username | 1. Leave username empty 2. Enter password 3. Click Login | Username: Blank , Password: secret_sauce | Username required error should appear | Error message "Username is required" was displayed when username field was empty. | Pass
TC-006 | TS-006 | Login | Verify login with empty password | 1. Enter username 2. Leave password empty 3. Click Login | Username: standard_user ,Password: Blank | Password required error should appear | Error message "Password is required" was displayed when password field was empty | Pass
TC-007 | TS-007 | Login | Verify login with empty fields | 1. Leave both fields empty 2. Click Login | Blank username and password | Validation message should appear | Error message "Username is required" was displayed when both username and password fields were empty. | Pass
TC-008 | TS-008 | Login | Verify error message for failed login | 1. Enter incorrect credentials 2. Click Login | Invalid credentials | Appropriate error message should display | Login failed and appropriate error message was displayed for invalid credentials. | Pass
TC-009 | TS-009 | Login | Verify locked user cannot login | 1. Enter locked user credentials 2. Click Login | Username: locked_out_user , Password: secret_sauce | User should not login and locked message should display | Locked out user was unable to login and locked user error message was displayed. | Pass
TC-010 | TS-010 | Login | Verify password characters are hidden | 1. Enter password in password field | secret_sauce | Password should appear masked | Password characters were hidden/masked while entering password. | Pass
Product Module Test Cases
Test Case ID | Scenario ID | Module | Test Case Description | Test Steps | Test Data | Expected Result | Actual Result | Status
TC-011 | TS-011 | Products | Verify products are displayed after successful login | 1. Login with valid credentials 2. Observe Products page | standard_user / secret_sauce | Products page should be displayed successfully | Products page was displayed successfully after login. | Pass
TC-012 | TS-012 | Products | Verify product names are displayed | 1. Login 2. Check product list | N/A | All available products should display their names | All products displayed with their names. | Pass
TC-013 | TS-013 | Products | Verify product images are displayed | 1. Login 2. Check product images | N/A | Product images should be visible correctly | Product images were displayed correctly. | Pass
TC-014 | TS-014 | Products | Verify product prices are displayed | 1. Login 2. Check product prices | N/A | Product prices should be displayed for each product | Product prices were displayed correctly. | Pass
TC-015 | TS-015 | Products | Verify product descriptions are displayed | 1. Login 2. Check product descriptions | N/A | Each product should have a description | Product descriptions were displayed correctly. | Pass
TC-016 | TS-016 | Products | Verify Add to Cart button functionality | 1. Login 2. Select any product 3. Click Add to Cart | Product: Sauce Labs Backpack | Product should be added to cart successfully | Product was added successfully to the cart. | Pass
TC-017 | TS-017 | Products | Verify Remove button after adding product | 1. Add product to cart 2. Click Remove button | Product added | Product should be removed from cart | Product was removed successfully. | Pass
TC-018 | TS-018 | Products | Verify multiple products can be added to cart | 1. Add multiple products 2. Open cart | Multiple products | All selected products should be added to cart | Multiple products were added successfully to the cart. | Pass
TC-019 | TS-019 | Products | Verify cart badge count updates after adding product | 1. Add product to cart 2. Observe cart icon | One product added | Cart badge should show correct quantity | Cart badge count updated correctly after adding products. | Pass
TC-020 | TS-020 | Products | Verify product sorting by Name A-Z | 1. Login 2. Open filter dropdown 3. Select Name A-Z | Sort: Name A-Z | Products should display in ascending alphabetical order | Products were sorted successfully from A-Z. | Pass
TC-021 | TS-021 | Products | Verify product sorting by Name Z-A | 1. Login 2. Select Name Z-A sorting | Sort: Name Z-A | Products should display in descending alphabetical order | Products were sorted successfully from Z-A. | Pass
TC-022 | TS-022 | Products | Verify product sorting by price low to high | 1. Open sorting dropdown 2. Select Price Low to High | Sort: Price Low to High | Products should arrange from lowest price to highest price | Products were sorted successfully by price Low to High. | Pass
TC-023 | TS-023 | Products | Verify product sorting by price high to low | 1. Open sorting dropdown 2. Select Price High to Low | Sort: Price High to Low | Products should arrange from highest price to lowest price | Products were sorted successfully by price High to Low. | Pass
Shopping Cart Module Test Cases
Test Case ID | Scenario ID | Module | Test Case Description | Test Steps | Test Data | Expected Result | Actual Result | Status
TC-024 | TS-024 | Cart | Verify added product is displayed in cart | 1. Login with valid credentials 2. Add a product to cart 3. Open cart | Product: Sauce Labs Backpack | Selected product should be displayed in shopping cart | Added product was displayed successfully in the shopping cart with correct details. | Pass
TC-025 | TS-025 | Cart | Verify product details in cart | 1. Add product to cart 2. Open cart 3. Check product information | Added product | Product name, image, description, and price should be correct | Product name, description, and price were displayed correctly, but product image was not displayed in the cart. | Fail
TC-026 | TS-026 | Cart | Verify Remove button functionality in cart | 1. Add product to cart 2. Open cart 3. Click Remove button | Product added in cart | Product should be removed successfully from cart | Product was removed successfully from the shopping cart after clicking the Remove button. | Pass
TC-027 | TS-027 | Cart | Verify cart is empty after removing all products | 1. Add product(s) to cart 2. Remove all products | Multiple products | Cart should become empty after removing all items | All products were removed successfully and the cart became empty. | Pass
TC-028 | TS-028 | Cart | Verify Continue Shopping button functionality | 1. Open cart page 2. Click Continue Shopping button | N/A | User should be redirected back to Products page | Continue Shopping button redirected the user back to the Products page successfully. | Pass
TC-029 | TS-029 | Cart | Verify Checkout button redirects to checkout page | 1. Add product to cart 2. Open cart 3. Click Checkout button | Product added | Checkout Information page should open | Checkout button redirected the user to the Checkout Information page successfully. | Pass
TC-030 | TS-029 | Cart | Verify multiple products are displayed correctly in cart | 1. Add multiple products 2. Open cart | Multiple products | All selected products should be displayed correctly | Multiple selected products were displayed correctly in the shopping cart. | Pass
TC-031 | TS-024 | Cart | Verify cart badge count after adding multiple products | 1. Add multiple products 2. Check cart icon badge | 2 or more products | Cart badge should show correct number of items | Cart badge displayed the correct number of added products. | Pass
TC-032 | TS-025 | Cart | Verify product price remains unchanged in cart | 1. Add product 2. Open cart 3. Compare product price | Product price | Product price should match the product listing page | Product prices remained the same in the cart as displayed on the Products page. | Pass
TC-033 | TS-028 | Cart | Verify checkout button is visible when product exists | 1. Add product 2. Navigate to cart | Product added | Checkout button should be visible and clickable | Checkout button was visible and clickable when products were available in the cart. | Pass
Checkout Information Module Test Cases
Test Case ID | Scenario ID | Module | Test Case Description | Test Steps | Test Data | Expected Result | Actual Result | Status
TC-034 | TS-030 | Checkout | Verify checkout with valid customer information | 1. Login 2. Add product to cart 3. Click Checkout 4. Enter customer details 5. Click Continue | First Name: NoorLast Name: ArbabPostal Code: 12345 | User should proceed to Checkout Overview page successfully | User entered valid checkout information and was successfully redirected to the Checkout Overview page. | Pass
TC-035 | TS-031 | Checkout | Verify checkout without entering first name | 1. Go to Checkout page 2. Leave First Name empty 3. Enter other details 4. Click Continue | First Name: Blank | Validation message should be displayed for First Name field | Validation message "First Name is required" was displayed when First Name field was empty. | Pass
TC-036 | TS-032 | Checkout | Verify checkout without entering last name | 1. Go to Checkout page 2. Enter first name 3. Leave Last Name empty 4. Enter postal code 5. Click Continue | Last Name: Blank | Validation message should be displayed for Last Name field | Validation message "Last Name is required" was displayed when Last Name field was empty. | Pass
TC-037 | TS-033 | Checkout | Verify checkout without entering postal code | 1. Go to Checkout page 2. Enter first and last name 3. Leave Postal Code empty 4. Click Continue | Postal Code: Blank | Validation message should be displayed for Postal Code field | Validation message "Postal Code is required" was displayed when Postal Code field was empty. | Pass
TC-038 | TS-034 | Checkout | Verify checkout with all fields empty | 1. Open Checkout page 2. Leave all fields empty 3. Click Continue | All fields blank | Required field validation message should appear | Validation message was displayed when all checkout fields were left empty. | Pass
TC-039 | TS-034 | Checkout | Verify checkout with spaces in input fields | 1. Enter spaces in all fields 2. Click Continue | First Name: " "Last Name: " "Postal Code: " " | Application should validate empty/invalid input | System displayed validation message when invalid empty spaces were entered in checkout fields. | Pass
TC-040 | TS-030 | Checkout | Verify user can enter valid characters in First Name field | 1. Enter valid name 2. Move to next field | First Name: Noor | Name should be accepted successfully | First Name field accepted valid characters successfully. | Pass
TC-041 | TS-030 | Checkout | Verify user can enter valid characters in Last Name field | 1. Enter valid last name | Last Name: Arbab | Last name should be accepted successfully | Last Name field accepted valid characters successfully. | Pass
TC-042 | TS-030 | Checkout | Verify postal code accepts valid input | 1. Enter valid postal code | Postal Code: 12345 | Postal code should be accepted successfully | Last Name field accepted valid characters successfully. | Pass
TC-043 | TS-035 | Checkout | Verify Cancel button functionality | 1. Open Checkout page 2. Click Cancel button | N/A | User should return to Cart page | Cancel button redirected the user back to the Cart page successfully. | Pass
Checkout Overview Module Test Cases
Test Case ID | Scenario ID | Module | Test Case Description | Test Steps | Test Data | Expected Result | Actual Result | Status
TC-044 | TS-036 | Checkout Overview | Verify product details are displayed on overview page | 1. Add product to cart 2. Complete checkout information 3. Click Continue | Product: Sauce Labs Backpack | Selected product details should be displayed correctly | Product details were displayed successfully on the Checkout Overview page. | Pass
TC-045 | TS-036 | Checkout Overview | Verify product name on overview page | 1. Add product 2. Go to checkout overview 3. Compare product name | Selected Product | Product name should match the selected product | Product name was displayed correctly and matched the selected product. | Pass
TC-046 | TS-036 | Checkout Overview | Verify product price on overview page | 1. Add product 2. Navigate to overview page 3. Check price | Product Price | Product price should match cart price | Product price was displayed correctly and matched the cart price. | Pass
TC-047 | TS-037 | Checkout Overview | Verify payment information is displayed | 1. Complete checkout information 2. Open overview page | N/A | Payment information should be displayed | Payment information was displayed successfully on the Checkout Overview page. | Pass
TC-048 | TS-038 | Checkout Overview | Verify shipping information is displayed | 1. Complete checkout information 2. Open overview page | N/A | Shipping information should be displayed | Shipping information was displayed successfully on the Checkout Overview page. | Pass
TC-049 | TS-039 | Checkout Overview | Verify tax amount is displayed | 1. Add product 2. Go to checkout overview | Product added | Tax amount should be displayed correctly | Tax amount was displayed correctly on the Checkout Overview page. | Pass
TC-050 | TS-040 | Checkout Overview | Verify total amount calculation | 1. Add product 2. Check item total 3. Check tax 4. Verify final total | Product with price | Total amount should equal item total + tax | Total amount was calculated correctly including item price and tax. | Pass
TC-051 | TS-041 | Checkout Overview | Verify Finish button completes order | 1. Complete checkout process 2. Click Finish button | Valid checkout data | Order should be completed successfully | Order was completed successfully after clicking the Finish button. | Pass
TC-052 | TS-042 | Checkout Overview | Verify Cancel button functionality | 1. Navigate to checkout overview 2. Click Cancel | N/A | User should return to Products page | Cancel button redirected the user back successfully. | Pass
TC-053 | TS-041 | Checkout Overview | Verify order cannot be completed without product | 1. Open checkout overview without product (if possible) 2. Try Finish | No product | Application should prevent invalid order completion | User was able to proceed with checkout and complete order even when the cart was empty. | Fail
Order Confirmation Module Test Cases
Test Case ID | Scenario ID | Module | Test Case Description | Test Steps | Test Data | Expected Result | Actual Result | Status
TC-054 | TS-043 | Order Confirmation | Verify order success message is displayed | 1. Complete checkout process 2. Click Finish button | Valid order | Order confirmation message should be displayed | Order confirmation message was displayed successfully after completing the order. | Pass
TC-055 | TS-043 | Order Confirmation | Verify confirmation page title | 1. Complete order 2. Check confirmation page | Completed order | Confirmation page title should be displayed correctly | Order confirmation page title was displayed correctly. | Pass
TC-056 | TS-044 | Order Confirmation | Verify Back Home button functionality | 1. Complete order 2. Click Back Home button | Completed order | User should be redirected to Products page | User was redirected successfully to the Products page after clicking Back Home. | Pass
TC-057 | TS-043 | Order Confirmation | Verify order completion message content | 1. Complete checkout 2. Read confirmation message | Completed order | Confirmation message should contain correct information | Order completion message was displayed with correct information. | Pass
Navigation Menu Module Test Cases
Test Case ID | Scenario ID | Module | Test Case Description | Test Steps | Test Data | Expected Result | Actual Result | Status
TC-058 | TS-045 | Menu | Verify menu opens successfully | 1. Login 2. Click menu icon | N/A | Side menu should open successfully | Navigation menu opened successfully after clicking the menu icon. | Pass
TC-059 | TS-046 | Menu | Verify menu closes successfully | 1. Open menu 2. Click close button | N/A | Side menu should close successfully | Navigation menu closed successfully after clicking the close button. | Pass
TC-060 | TS-047 | Menu | Verify All Items option functionality | 1. Open menu 2. Click All Items | N/A | User should be redirected to Products page | User was redirected successfully to the Products page after clicking the All Items option. | Pass
TC-061 | TS-048 | Menu | Verify About option functionality | 1. Open menu 2. Click About | N/A | User should navigate to About page | User was redirected successfully to the About page after clicking the About option. | Pass
TC-062 | TS-049 | Menu | Verify Logout functionality | 1. Login 2. Open menu 3. Click Logout | Valid user | User should be logged out and redirected to login page | User was logged out successfully and redirected to the Login page after clicking Logout. | Pass
TC-063 | TS-050 | Menu | Verify Reset App State functionality | 1. Add product to cart 2. Open menu 3. Click Reset App State | Product added | Cart should be reset successfully | Application state was reset successfully and cart items were removed after clicking Reset App State. | Pass

## Bug Report
Bug ID | Module | Bug Title | Severity | Priority | Steps to Reproduce | Expected Result | Actual Result | Status | Screenshot
BUG-001 | Shopping Cart | Product image is not displayed in cart | Medium | Medium | 1. Login to application. 2. Add any product to cart. 3. Open Cart page | Product image should be displayed with product details in the cart | Product name, price, and description were displayed, but product image was missing | Open | BUG-001_Product_Image_Not_Displayed.png
BUG-002 | Checkout | User can complete order with empty cart | High | High | 1. Login to application. 2. Open Cart page. 3. Remove all products. 4. Proceed to checkou. t5. Complete order | System should prevent checkout and order completion when cart is empty | User was able to proceed with checkout and complete order even when the cart was empty | Open | BUG-002_Empty_Cart_Order.png

## RTM
Requirement ID | Requirement Description | Test Scenario ID | Test Case ID | Test Result
REQ-001 | User should be able to login with valid credentials | TS-001 | TC-001 | Pass
REQ-002 | System should display error message for invalid login credentials | TS-002 | TC-002, TC-003, TC-004 | Pass
REQ-003 | User should see products after successful login | TS-003 | TC-011 | Pass
REQ-004 | User should be able to view product details | TS-004 | TC-012, TC-013, TC-014, TC-015 | Pass
REQ-005 | User should be able to add and remove products from cart | TS-005 | TC-016, TC-017 | Pass
REQ-006 | User should be able to view cart details | TS-006 | TC-024, TC-025 | Fail (BUG-001)
REQ-007 | User should be able to proceed to checkout | TS-007 | TC-029, TC-034 | Pass
REQ-008 | Checkout form should validate required fields | TS-008 | TC-035, TC-036, TC-037, TC-038 | Pass
REQ-009 | User should see checkout overview information | TS-009 | TC-044, TC-045, TC-046, TC-047, TC-048 | Pass
REQ-010 | System should calculate tax and total amount correctly | TS-010 | TC-049, TC-050 | Pass
REQ-011 | User should be able to complete order successfully | TS-011 | TC-051, TC-054 | Pass
REQ-012 | System should prevent order completion without products | TS-012 | TC-066 | Fail (BUG-002)
REQ-013 | User should be able to logout successfully | TS-013 | TC-062 | Pass
REQ-014 | Navigation menu options should work correctly | TS-014 | TC-058, TC-059, TC-060, TC-061, TC-063 | Pass